## Example--School-year Project
Activities | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October
Contact potential partners & MoMS to develop ideas for content creation including platform type and research | July: MoMS sends acceptance notices
Develop proposal to submit to MoMS--proposal guidelines, support letters, tentative budget | July: MoMS notifies participant sites
Create tentative timeline and schedule (use this document or other preference)--determine tech needs | July: MoMS submits funding request; August: Finalize partners and youth; September: Announce project w/ press release
Introduce project to youth--SI exhibition content, Quality Story Characteristics, and story ideas and/or examples, distribute youth releases | September: Field trip to history org or site, youth and org brainstorm ideas together
Training and Research--historical context of topic, storytelling, interviewing, production | May: Review project deliverables!; September: Field Practice--conduct test interviews (w/each other), test equipment (if available) in different conditions (outside/inside)
Explore images, maps, newspapers, etc for stories--learn about fair use, public domain and Creative Commons | June: Remember to collect youth releases!; October: Use national repositories like Smithsonian, Library of Congress, National Archives and others like Wikimedia
Contact potential interviews based on youth interests in consultation with organization and other partners | June: Finalize your equipment list!; November: MoMS sends award notices; December: HOLIDAYS! Scheduling will be difficult
Timeline and Plan Revisiondue, buy equipment w/funds, develop storylines/storyboards | June: Fill out your budget and save receipts!; January: Funds become available
Conduct interviews and record b-roll footage--Note: new info may alter storyline and require new research | June: Keep interviews short and go back for more info if needed!; January: Collect interview multimedia releases, select images/music with permissions or get permission for history org media
Production--assemble all interviews and multimedia into storylines and start editing | June: Trim down original story plans. Don't get overwhelmed with ideas!; February: Plan premiere of stories with local partners, determine social media plan (with MoMS) and think about long-term plans for content and equipment
Premiere stories--hold event for youth with partners, interviewees, businesses, local orgs that helped | June: Keep partners informed and plan premiere events with them!; May: Share stories on MoMS site, etc
Finalize deliverables--youth releases, interview releases, final budget, Technology Log, Program Log | July: Delays are normal. Keep in touch with MoMS if you get stuck or need more time!; June: Send to MoMS for grant balance; August: MoMS FINAL PROJECT DEADLINE; September: MoMS submits final report to funders and councils
Key Deliverables and Deadlines
·Bibliography and primary sources including interviews: [date]
·Storyline and/or storyboard: [date]
·Digital multimedia stories: [date]
·Presentation of the stories to [your cultural organization partner]: [date]
NOTE: Italics reference available resources/document deliverables: | April: https://museumonmainstreet.org/content/stories-yes-resources

## Example--Short-term Project
Activities | ADMIN | EDUCATOR | Day 1-3 | Days 4-6 | Days 7-9 | Days 10-12 | Days 13-15 | Days 16-18 | Days 19-21
Create detailed timeline and schedule (use this document or other preference)--determine equipment |  | Announce project w/ press release |  |  | See also: Sample Equipment list and Storytelling Field Guide
Timeline and Plan Revisiondue in January, buy equipment w/funds, determine content outputs | Make sure kids have dedicated time for project, usually within scope of existing camp or activity |  |  |  | See also: Documents for Grantees
Introduce history content to youth, story ideas, show exactly what you want made, distribute youth releases | Find one location for research, interviews, editing; schedule interviews | CURRICULA: Topic and Conducting Research, Story, Interviewing, Images and permissions | WORKSHOPS: conduct test interviews (w/each other), test equipment in different conditions |  | See also: MoMS exhibition script, Quality Story Characteristics
Training and Research--historical context of topic, storytelling, interviewing, production |  |  |  |  | See also: Sample Timeline/Workshop Schedule, Learning Lab training modules
Create narrative on topic and keep topic small--use audio interviews and still images to keep tech simple | Research repositories in public domain that have images for your topic |  |  | Create 2-5 min storyboard with images (film b-roll if weather, time allow) |  | See also: Storyboard workshop template, Learning Lab
Conduct interviews--interview few people per story and prepare questions ahead (collect b-roll footage but not too much) | Confirm interview schedule | Produce questions for each type of interview |  |  | Have multiple kids participate by using tech and asking questions |  | See also: Learning Lab, Field Guide
Production--assemble all digital content and mark what fits storyboards, begin editing | Make sure deliverables are being met in process | Ensure youth permissions are collected |  |  |  | Some kids may transcribe while others edit; additional content may be needed too |  | See also: Learning Lab, Field Guide
Build in additional time for unexpected things like scheduling conflicts, re-shoots, and additional research or quality check | [6 empty] | Allow time for feedback, particularly if kids are working in teams |  | See also: Learning Lab, Field Guide
Send stories to MoMS and Premiere them--hold event for youth with partners, interviewees, businesses, local orgs | Finalize deliverables, distribute stipends; plan how to repeat program, increase partners | Ensure that stories are ready for public and that all minors have permissions and credits | [5 empty] | Share stories on MoMS site and local premiere
Deliverables due--youth releases, interview releases, final budget, Technology Log, Program Log | [8 empty] | Send to MoMS for grant balance
NOTE: Italics reference available resources/document deliverables: | https://museumonmainstreet.org/content/stories-yes-resources